## 1_Features-Deliverables
Feature / Deliverable | Description | Included in MVP | Included in v1 / later | Dependencies / Notes
Year-long schedule generation | Generate an entire year respecting vacations, FTE/PT rules, eligibility, and fairness. | MVP |  | Requires roster, shift catalog, vacation/PT inputs.
Month-only generation | Support month-by-month generation for testing or incremental rollout. | MVP |  | Same engine, limited scope.
Vacation intake (ranked choices) | Users submit 3 ranked vacation weeks per month; engine resolves fairly. | MVP |  | Fairness ledger tie-breaks.
PT day allocation (auto-assign) | Auto-balance part-time days per FTE across weekdays. | MVP |  | Weekday balance limits.
PT day selection (user-pick mode) | Users pick PT days; UI enforces weekday balance. |  | v1 | Toggle between auto vs user-pick per group.
Subspecialty eligibility mapping | Shift types restricted to eligible subspecialties or named users. | MVP |  | From ‘Shifts’ sheet & admin overrides.
Named eligibility exceptions | Certain shifts (e.g., MA1 subset, Coiling) restricted to specific rads. | MVP |  | Requires named lists from admin.
Swap (same shift type, same day) | Initiate swap with an eligible counterpart for the same shift/day. | MVP |  | Sequential notifications to candidates.
Swap (equivalent shift types, multi-target) | Swap across defined equivalence sets; offer to multiple targets sequentially. |  | v1 | Needs Equivalence Set config.
Giveaway (weekend call, etc.) | Give away allowed shift types to eligible pool (sequential offers). | MVP |  | List of giveaway-eligible shifts required.
Away windows | Block receiving swap/giveaway requests on specified dates. |  | v1 | Per-user setting.
Admin overrides + local re-balance | Manual edits with local re-balancing to keep fairness. | MVP |  | Audit trail for changes.
One-way Google Calendar sync | Push published assignments to each user’s Google Calendar. | MVP |  | OAuth per user; ICS fallback.
Reporting: monthly CSV + YTD | Per-user shift counts & $ totals; group roll-ups; YTD totals. | MVP |  | Dollar value table needed for $ totals.
Reporting: PDF outputs | Nicely formatted PDFs for bookkeeper and leadership. |  | v1 | Branding and summary pages.
Audit logging | Who changed what, when (engine runs, overrides, approvals). | MVP |  | Immutable log entries.
Resident-call plan (free) | Lightweight plan targeting residency call scheduling. |  | v1 | Go-to-market channel.
Billing (per-group or per-user) | Stripe-based subscriptions and plan management. |  | v1 | Pricing model decision.
Optimizer (OR-Tools) | Constraint programming solver for tighter optimality. |  | v1.5+ | Toggle vs heuristic engine.
AI linting (suggested fixes) | Post-gen checks suggesting swaps to reduce risk/fatigue. |  | v1.5+ | Optional and explainable.

## 2_Knowns-&-Assumptions
Legend: | Confirmed | Assumed (highlighted) | Unclear / Needs validation (highlighted)
Item | Current detail | Status | How we know / assumption | Notes
Roster | 27 radiologists with subspecialties (e.g., Neuro, Body, Chest/Body, XRUS, IR/Body). | Confirmed | File: Shift hours (1).xlsx ▸ Radiologists | Mixed subspecialty tags exist (e.g., Chest/Body, MSK/Body).
Shift catalog | 23 shift types with hours and subspecialty gating. | Confirmed | File: Shift hours (1).xlsx ▸ Shifts | Includes late blocks (Body/Neuro 16–18, 18–21).
Schedule layout pattern | Weekly sheets like June 2-8, June 9-15 … | Confirmed | File: June 2025 sked v April 1.xlsx | Columns: Week of, Mon–Fri, Sat/Sun; cells contain initials & notes.
Neuro-only shifts | Neuro 1–4 restricted to neurorads. | Confirmed | Transcript + Shifts sheet | From transcript: 'Neural 1234 are only done by neuro'.
IR vascular | Vascular on-site restricted to IR. | Confirmed | Transcript + Shifts sheet
Body-only modalities | CT/US, MSK, Body MRI, Body volume support by Body. | Confirmed | Transcript + Shifts sheet
Chest-only cardiac | Cardiac CT/MRI by Chest rads. | Confirmed | Transcript + Shifts sheet
General X-ray | Anyone (commonly covered by Body). | Confirmed | Transcript + Shifts sheet | Eligible = Any; cultural norm = Body covers often.
Coiling (INR) | INR-only; currently one named person. | Needs validation | Transcript | We need the named person & coverage plan during their vacation.
MA1 named eligibility | MA1 is 'Any' but may be a restricted named subset. | Unclear | Transcript | Need explicit named list if it’s not truly Any.
Vacation policy | 1 week/month; users submit ranked choices; fairness across year. | Confirmed | Client’s feature list + transcript | Engine uses fairness to resolve ties.
Vacation fairness scoring | Exact tie-break scoring/decay. | Assumed | Design default | Documented VFS: 0/1/2/3 with decay after tie-win.
PT days per FTE | Mapping for 60/70/80/90/100%. | Unclear | Transcript (20% ≈ 1 day/wk) → needs table | Temporary config table proposed.
PT weekday balance | Limit Mon/Fri bias. | Assumed | Design default | Mon/Fri ≤ others +1 within month.
Equivalence sets | Which shift types are swappable equivalents. | Unclear | Not in files/transcript | Needed to enable cross-type swaps.
Giveaway-eligible shifts | Which shifts (e.g., weekend call) can be given away. | Unclear | Not in files/transcript | Needed for giveaway rules.
Dollar values | Per shift (and weekend/holiday premiums?). | Unclear | Not in files/transcript | Required for payout reports.
Holidays | Ontario stat list & coverage/value rules. | Unclear | Not in files/transcript | Default: normal coverage, no premium.
Rest/sequence caps | Max consecutive nights; night→day rest, weekend call caps. | Unclear | Not in files/transcript | Default: no special caps (MVP avoids stacking heuristically).
Coverage exceptions | Any shifts allowed to go uncovered. | Unclear | Not in files/transcript | Default: all defined instances must be filled.
Fellows | Names, eligibility, and vacation/PT rules. | Unclear | Not in files/transcript | Default: none for first run.
Calendar naming | Event title/desc conventions. | Assumed | Design default | Title: '<Shift Code> — <Site/Notes>'; ICS fallback.
Billing mode | Per-group vs per-user for this client. | Unclear | Not in files/transcript | Default: per-group for simplicity.
Timezone & week start | America/Toronto; week starts Monday. | Assumed | Design default
Initials mapping & flags | Initials↔full name map; meanings of '*', '+late', 'rds', '(INR call)'. | Unclear | From June sheet notation | We’ll ingest notes as free-text until defined.
Swap approval thresholds | When chief approval is required. | Assumed | Design default | Any soft-rule violation → chief approval; hard rules never broken.

## 3_Unknowns-Defaults
Topic / Decision Needed | What we need from client | Default applied now | Why this default | Impact / Priority
Dollar values per shift | Provide $ per shift and any weekend/holiday premiums. | Default $0 for all except a single Weekend Call rate. | We need a table to compute payouts; a single call rate allows reports to function until finalized. | Medium
Giveaway-eligible list | Confirm which shift types can be given away vs swap-only. | Weekend call giveaway; others swap-only. | Matches your note; minimizes risk until rules clarified. | Medium
MA1 named eligibility | List who can take MA1 (if not truly 'Any'). | Treat as 'Any' until named list provided. | Avoids blocking assignments; easy to tighten later. | Medium
Coiling coverage | Name the INR person(s) and backup plan. | Assume 1 named radiologist; no backup. | We must warn on uncovered days; needs policy. | High
PT mapping per FTE | Days/month for 60/70/80/90/100%. | Table: 100%=0; 90%=2; 80%=4; 70%=6; 60%=8. | Implements transcript heuristic (~1 day/week per 20%). | High
PT weekday balance | Define exact cap on Mon/Fri vs others. | Mon/Fri ≤ others+1 per month. | Prevents 'every Friday off' clustering. | Medium
Equivalence sets | Which shift types can swap across types. | None (same-type only) in MVP. | Safe until you specify equivalences. | Medium
Rest/sequence caps | Max consecutive nights; rest before day; weekend call caps. | No hard caps; heuristic avoids stacks. | We’ll add constraints once numbers are known. | Low
Holidays | Holiday dates + coverage/value rules. | Ontario stats; no premium; normal coverage. | Safe baseline; easy to update. | Low
Coverage exceptions | Any shifts allowed to be unfilled on specific dates. | None allowed. | Ensures full coverage; admin can override if needed. | Medium
Fellows | Names, eligibility, vacation/PT rules. | No fellows in first run. | Add when provided. | Medium
Calendar naming | Exact event title/desc/location style. | Title '<Shift Code> — <Site/Notes>' | Readable defaults; consistent. | Low
Billing mode | Per-group vs per-user. | Per-group. | Fastest to deploy and invoice. | Low
Initials & flags | Initials map; flags meanings ('*', '+late', 'rds'). | Import flags as notes only. | Avoids logic errors until defined. | Medium
Swap approval thresholds | Define when chief must approve. | Any soft-rule violation. | Keeps governance strong until tuned. | Medium